## Sheet1
Feature	Description	Status	Priority	Last Updated
Events I	* “Boots worn out” Pace auto set to slowest while without boots. / * “Lost” clock advances by 20-80 minutes. / * “Harsh weather” lose health. / * “Robber” get robbed of some materials and/or health, food, goods. / * “Sick” Stamina regeneration halved while sick. Sick can be cured by sitting still for cumulative 12-36 hours.	Todo	1
Events II	* Six : Player dies if outside at 12AM, 6AM, 12PM, or 6PM.	Todo	1
Encumbrance	How much equipment party has affects how fast you can go	Todo	1	03/16/23
Equipment II	Trade goods, wheelbarrows, extra people in the party, kalnotes	Todo	1	03/16/23
Trading	Trade goods for currency at settlements	Todo	1	03/16/23
Scavenging	Find goods in ruins. The further you are from a settlement or further along in general, better goods, more danger.	Todo	1	03/16/23
Add configuration manager	https://github.com/CODESOLE/ini-parser-cpp	Todo	2	06/19/22
Lighting system	https://www.youtube.com/watch?v=fc3nnG2CG8U&t=1005s	Todo	4	4/2/2021
Edge map for ray tracing	Consolidate all collisionable tiles on the map into an edge map for the purpose of ray casting / line of sight	Todo	5
Upgrade Pathfinding	Use post processing on A*, string pulling method or greedy method	Todo	8	06/19/22
AI: Run for Cover	An AI Behavior where AI determines a direction + distance from which a threat is and moves to the closest place that puts a collision between them and the threat while not violating some standoff distance from the threat.	Todo	8	4/2/2021
Exploration: Forgotten HOPLON	Have many levels of digging through rubble etc. and hidden caves under the mountain. Eventually find the particle lancer.	Todo	10	4/2/2021
Breeding Animals	Find Six-Proof animals outside. Breed them into weirder creatures. Inspiraton: Dragon Quest	Todo	10	4/2/2021
Crops Growing	Grow crops	Todo	10	4/2/2021
Burrows	Dwarf Fortress burrows/restricted area.	Todo	10	4/2/2021
Faction System	Dwellers have factional preferences. Factions exist based on critical mass of dwellers with a preference. Happiness is combination of personal needs and factional fulfillment. High priority as could be a selling feature, differentiator from DF or Rimworld.	Todo	10	4/2/2021
Multithreading	Done: ComponentArrays are mutex locked. / Done: ComponentArrays should allow check out of individual components rather than block entire array for one index being checked out. Have a "master" lock for when components are being added/deleted (the indexes themselves are moving around) vs an individual lock for each entry in the array. / Todo: Actually use more than one thread in game loop	In Work	4	4/2/2021
Region/Map System	Inspiration: region system from Rimworld. Break the world up into 16 by 16 tile blocks. Instead of updating attributes for every tile / every frame, each block will have a flag indicating that the block needs to be updated. Then every tile inside a block is updated. / Use this for when to generate new edges for raytracing. / Have a system that monitors all the tile components and consolidates their attribute into a map singleton that can have meta data.	In Work	10	4/2/2021
Save/Load System	Self explanatory. Idea: Use JSON to offload all entities in the game to a file and any other state held by the Coordinator. / In Progress: using nlohmann json library for json. / Plan: Have a "saveable" component which marks entities as saveable. Have SaveSystem which responds to SaveEvent -> / Go through all saveable entities, call Coordinator getAllData, and dump to JSON file.	Done	1	4/2/2021
Event System	Create a Component called "Event" that has vector of Component,Entity,System. / The idea being that any behavior in the game can be accomplished with a series of system, / entities, and components. Each existing system can have logic to make sense of what is in those vectors.	Done	1	4/2/2021
Switching State	Should different states use different coordinators? Or should entities simply be added/removed from the coordinator and systems deactivated? / Should the texture manager be moved from Coordinator -> Some new state manager? / Probably want textures not in use to be removed from memory ... but maybe not. I don't use many textures (yet). / How to tell when textures won't be needed for a long time? / Extract events + their data from the coordinator and store somewhere else between states.	Done	1	4/2/2021
InputHandlingSystem	Do a while(SDL Event) and pass it all to a new entity. Entity should be an "event"	Done	1	4/2/2021
Select objects	Objects can be clicked on. Will display some information depending on context.	Done	1	4/2/2021
Track which components an entity has	Need a better solution than checking for each component for each entity	Done	1	4/2/2021
In game menu	Pressing escape brings up menu	Done	1
Fix collision box of agents	Use a small circle collision box instead of a square that gets stuck on two solid tiles with one tile gap between them. Or, remove real continuous movement and have agents jump from tile to tile.	Done	1	06/19/22
World Time	A component/system that tracks time	Done	1	10/25/22
Party Resources	Track how much food, water, etc the party has.	Done	1
Parallax System	System and components to have a scrolling background.	Done	1
Progress Bars	New UI element	Done	1	03/01/23
Equipment I	Like Oregon Trail or the car card game. Disasters that need to be countered by items. Select items at game start with budget. Trade and scavenge later. / * Boots: Counter “Boots worn out”. / * Medicine: Used to counter “Sick”. / * Stimulant: Can be used to ignore status hindering pace for 3 hours. / * GPS: Can be used to counter “Lost”. 1 time use. (Eventually use batteries) / * Fire Blanket: Used to counter harsh weather. / * Gun: Counter robber.	Done	1
Director System I	ECS System to issue events to player party	Done	1	03/01/23
Camera Tracking	Rectangle determines what is drawn to screen and can be assigned to "track" any entity with a renderable component	Done	2	4/2/2021
Pathfinding	A* or Hierarchical A*.	Done	2	4/2/2021
Multiple sprites per renderable	For changing orientation, animations, etc. Have "active sprites" - a vector of sprites that is iterated through per configurable time interval. Multiple can be active at a time. "Walking left" "Running left" "using hands" "taking damage"	Done	2	4/2/2021
Save/Load Events	Cannot dump a function pointer to JSON. Need to rebuild events from JSON.	Done	2	04/02/22
MovementSystem	"Moveable" component. Should have subclasses for different types of movement that MovementSystem can handle individually. / Make sure the Parent moveable class is the signature for Movement system.	Done	3	4/2/2021
Move backward	Allow player to move backward	Todo	1	04/02/21
Quest: Thoreau	A poet NPC from HOPLON who is “out to observe the natural wonder of the world”. Player has to give him food, etc. and generally rescue him / Every time they meet or he will die.
Quest: Shipping Up To Boston	An NPC the player finds bleeding out next to a large tower. His party asked him to climb it to scout out the area, but he fell off. / 1. Give him a medkit for the leg wound. He will trade you a trade good (DVD) Enables you to find a prosthetic leg. / 2. He is using crutches next time you find him, but is exhausted. Giving him prosthetic leg helps him. / 3. Lying on the ground again. Bandits have stolen his prosthetic leg. Will trade you another DVD for a medkit. Says they sold it next town over, probably. / 4. Meet him in the next town over. Apparently they tried to sell, but the town ran them out when they found out they were bandits. He will follow them to Boston. / 5. Next find him hung up with a sign around his neck “This is what happens to Bandits.”
Quest: The Film Historian	An NPC interested in the history of film. Collects DVDs by Eve Cobbler (Adam Sandler). They do not have a DVD player though, so they want to / Get to HOPLON so they can watch the films once they’ve collected them all.

## Sheet2
Status
Todo
In Work
Verification
Done
Working